## Implementation plan
На грани провала | Name | Start Date | End Date | Исполнитель | % выполнения | Длительность выполнения | Задачи, предшествующие данной | Комментарии
| Implementation and testing | 2017-11-16 | 2018-01-25 |  | 4% | 51d
| Prototype implementation | 2017-11-16 | 2017-12-18 |  | 18% | 23d
| Platform installation and setup | 2017-11-16 | 2017-11-17 |  | 50% | 2d
| Database implementation | 2017-11-18 | 2017-12-18 |  | 50% | 22d
| Server subcomponents implementation | 2017-11-18 | 2017-12-18 |  |  | 22d
| Mobile app subcomponents implementation | 2017-11-18 | 2017-12-18 |  |  | 22d
| Prototype testing | 2017-11-20 | 2018-01-17 |  |  | 43d
| Unit testing | 2017-11-20 | 2017-12-29 |  |  | 30d
| Unit testing for database | 2017-11-20 | 2017-12-19 |  |  | 22d
| White box testing for the server subcomponents | 2017-11-20 | 2017-12-19 |  |  | 22d
| Bugs fixes in code, frameworks and structures | 2017-11-20 | 2017-12-19 |  |  | 22d
| Black box testing for the server subcomponents | 2017-12-20 | 2017-12-29 |  |  | 8d
| White box testing for the server subcomponents | 2017-11-20 | 2017-12-19 |  |  | 22d
| Bugs fixes in code, frameworks and structures | 2017-11-20 | 2017-12-19 |  |  | 22d
| Black box testing for the mobile app subcomponents | 2017-12-20 | 2017-12-29 |  |  | 8d
| Integration testing | 2017-12-30 | 2018-01-05 |  |  | 6d
| Data bottom up analysis - definition of the integration modalities | 2017-12-30 | 2018-01-01 |  |  | 2d
| Bottom up data integration testing | 2018-01-02 | 2018-01-05 |  |  | 4d
| Server bottom up analysis - definition of the integration modalities | 2017-12-30 | 2018-01-01 |  |  | 2d
| Bottom up server integration testing | 2018-01-02 | 2018-01-05 |  |  | 4d
| Bug fixes | 2018-01-02 | 2018-01-05 |  |  | 4d
| Mobile bottom up analysis - definition of the integration modalities | 2017-12-30 | 2018-01-01 |  |  | 2d
| Bottom up mobile integration testing | 2018-01-02 | 2018-01-05 |  |  | 4d
| Bug fixes | 2018-01-02 | 2018-01-05 |  |  | 4d
| System testing | 2018-01-06 | 2018-01-10 |  |  | 4d
| First Internal simulation (Server side analysis) | 2018-01-07 | 2018-01-07 |  |  | 1d
| First Internal simulation (Mobile App side analysis) | 2018-01-07 | 2018-01-07 |  |  | 1d
| Bug fixes | 2018-01-08 | 2018-01-10 |  |  | 3d
| Second Internal simulation (Mobile App side analysis) | 2018-01-11 | 2018-01-11 |  |  | 1d
| Bug fixes, Code inspection | 2018-01-11 | 2018-01-17 |  |  | 5d
| Concrete components integration testing | 2018-01-08 | 2018-01-16 |  |  | 7d
| Documentation and Demonstration | 2017-12-19 | 2018-01-25 |  |  | 28d
| First Internal Demonstration | 2018-01-13 | 2018-01-13 |  |  | 1d
| Second Internal Demonstration | 2018-01-19 | 2018-01-19 |  |  | 1d
| Implementation and Test deliverable (ITD), User manual | 2017-12-19 | 2018-01-08 |  |  | 15d
| Acceptance Test deliverable (ATD) | 2017-12-24 | 2018-01-12 |  |  | 16d
| Project presentation for Stakeholders | 2018-01-25 | 2018-01-25 |  |  | 1d

## Comments
Row 3 | Сохраняйте комментарии к задачам в обсуждениях. Обсуждения отлично подходят для сохранения адресов электронной почты, переписки внутри команды и быстрого обмена идеями. Вы также можете прикрепить документы непосредственно к обсуждению. | Alexandra Ragazhinskaya | 03/07/17 15:07
Row 4 | Сохраняйте комментарии к задачам в обсуждениях. Обсуждения отлично подходят для сохранения адресов электронной почты, переписки внутри команды и быстрого обмена идеями. Вы также можете прикрепить документы непосредственно к обсуждению. | Alexandra Ragazhinskaya | 03/07/17 15:07